Assessment Protocol

End-Process Assessment of 
ITN Campaign Distribution

Country and/or locations, Year

Note for users:

Text in blue italics should be customized to your needs.

Date

Table of Contents

Instructions for users	4

Abbreviations	5

1	Background	6

1.1	Introduction	6

1.2	Malaria, ITN and campaign overview	7

1.3	Objectives	7

2	Methods	8

2.1	Assessment design	8

2.2	Assessment Sites	8

2.3	Sample size	9

2.4	Sampling procedures	10

2.4.1	Stage one: selection of clusters	10

2.4.2	Stage two: selection of households	10

2.5	Assessment questionnaire	11

2.6	Assessment staff, recruitment and training	12

2.6.1	Staffing structure	12

2.6.2	Recruitment	12

2.6.3	Training	13

2.7	Field procedures	13

2.7.1	Preparation for cluster entry	14

2.7.2	Household consent and interviews	14

2.7.3	Data collection and data management and safety during fieldwork	14

2.7.4	Supervision and monitoring	15

2.8	Data management and analysis	15

2.8.1	Management of data private and security	16

2.8.2	Data processing and analysis	16

2.8.3	Data review and response, including lot investigations	20

2.9	Reporting and data archiving	20

2.9.1	Final reporting	20

2.9.2	Data availability	21

3	Ethical Considerations	21

3.1	Informed consent	21

3.2	Risks to participants and response	22

3.3	Beneficence (Maximizing Benefits and Minimizing Harm)	22

4	Collaborators and funding mechanisms	23

5	Budget	24

6	Timeline	25

7	Bibliography	27

8	Annexes	28

Assessment questionnaire	29

Participant information sheet	30

Participant consent form	32

# Instructions for users

This adaptable template provides guidance and content examples for the protocol to accompany an end-process assessment of ITN distribution, following Alliance for Malaria Prevention (AMP) recommendations. Documenting assessment procedures in the manner described here is good evaluation practice, regardless of whether submission to an ethical review committee will occur.

The intended audience for this document is national malaria programme staff and partners leading and supporting an end-process campaign assessment. When completed, the protocol will serve as the guiding document for assessment planning, budgeting and implementation, including data collection, analysis and reporting. Contexts vary and the protocol template should be adapted and modified to include any additional information needed.

Guidance on minimum content requirements for each section is provided in blue italic text.

Example content is provided for most sections following the guidance bullets. Users will need to adapt this text with their own narrative as appropriate.

Questions or feedback on the content and use of this template should be sent to info@allianceformalariaprevention.com.

This protocol template is part of a toolkit of material for programmes designing and implementing ITN campaign assessments (both end-process and in-process). Further material, including adaptable questionnaire files and analysis scripts is available at https://github.com/edsternberg/clqas-tools.

# Abbreviations

AMP	Alliance for Malaria Prevention

cLQAS	Cluster lot quality assurance sampling

HH	Household

HHR	Household registration

IT	Information technology

ITN	Insecticide treated nets

LQAS	Lot quality assurance sampling

M&E	Monitoring and evaluation

MoH	Ministry of Health

NGO	Non-governmental organization

NMP	National Malaria Programme

NMSP	National Malaria Strategic Plan

ODK	Open Data Kit

SBC	Social and behavioral change

WHO	World Health Organization

# Background

## Introduction

Maintaining high coverage of insecticide-treated nets (ITN) for populations in need is important to provide community-level protection from malaria vectors. Most national malaria programmes (NMP) include ITN distribution to communities as the primary vector control intervention in their national malaria strategic plans (NMSP) and many NMPs prioritize the use of ITN mass campaigns to rapidly and equitably achieve high levels of ITN access. However, in some cases, households (HH) do not receive any ITNs or receive an incorrect number of ITNs (fewer or more than planned in relation to the campaign ITN allocation rules), leading to lower than expected ITN coverage following campaigns. Reasons for the discrepancy between ITN mass distribution campaign plans and actual results may be due to real or perceived ITN shortages during distribution, or errors or inconsistencies in household registration (HHR) and/or ITN distribution activities.

NMPs identify the campaign strategy that best responds to geographic, operational and health security factors and, in conjunction with the campaign’s national coordinating committee, make a final determination on the approach to be implemented. Strategies for conducting ITN mass distribution campaigns currently include but are not limited to:

- A fixed-site distribution approach that includes a separate HHR process, in which a count of eligible household members is recorded and HHs receive a means of identification (e.g. QR code, bar code, other voucher) to exchange for an assigned number of ITNs at a pre-determined ITN distribution site, usually at a date closely following the HHR.

- A door-to-door approach in which HHR and distribution are conducted either during a single-phase campaign, which involves HHR and ITN distribution during  a single visit, or during a double-phase campaign, which involves a first visit to the HH to conduct HHR and a second visit for ITN distribution.

It is important that campaign teams support a smooth distribution process, including mobilization of the population to accept their allocated ITNs at the door, to visit their correct distribution sites, and to confirm that ITN recipients understand the procedures for them to receive their ITNs and what to do with the ITNs when they reach home. Additionally, data collection and accountability for ITNs distributed must be prioritized. With many hundreds of distribution points or pre-positioning sites where ITNs will be stored and managed, the risks for variable quality of the distribution and ITN accountability are high.

The quality of ITN distribution depends on:

- Well trained door-to-door distribution personnel

- Well organized distribution sites

- Availability of sufficient numbers and types of ITNs to meet the demand of every HH registered

- Effective SBC to ensure HHs are aware of the ITN campaign and know how to receive their ITNs, however distributed

- Effective microplanning of distribution site locations and hours to facilitate access

- Sufficient planning by campaign teams to identify and reach vulnerable groups and hard-to-reach populations with ITNs

Ensuring the quality of ITN distribution activities is vital to protect and maximize investments in malaria vector control. Conducting an operational assessment to track the quality and coverage of ITN distribution activities and to make recommendations for future corrective actions serves this goal by increasing population access to ITNs and improving the efficiency of ITN mass campaigns.

## Malaria, ITN and campaign overview

- Briefly describe the malaria situation in the country and the key interventions being deployed.

- Briefly describe the current ITN strategy, distribution channels and key indicators from population-based surveys and www.itnuse.org.

- Describe the rational for undertaking the in-process assessment, including any data or results from previous campaign activities as appropriate.

- Describe the strategy for the current ITN campaign, including plans for HHR and the ITN allocation strategy.

- List the campaign objectives and expected outcomes / targets.

- State the definition of “household” used by the campaign.

- State the eligibility criteria for HHR.

Example content omitted for this section.

## Objectives

- State the primary and secondary objectives for the assessment.

The primary objectives of the assessment are:

- Assess the quality of ITN distribution by comparing the number of campaign ITNs received against the number that should have been assigned based on the campaign allocation rules and the count of eligible household members recorded during household registration, for a sample of households.

- Describe the reasons why households did not receive the correct number of ITNs and share results with campaign leadership to inform recommendations for future campaigns.

Secondary objectives are:

- Estimate the level of ITN access among household members following ITN distribution.

- Estimate the level of ITN use the previous night among household members and describe reasons why people did not use an ITN.

- Classify pre-defined areas (lots) based on campaign performance (i.e. the number of households in a lot that did not receive the correct number of ITNs) to identify additional recommendations to strengthen future campaigns.

# Methods

## Assessment design

- Include a short paragraph that describes cluster LQAS.

- Describe the assessment approach.

- Describe the timing of the assessment in relation to the campaign activity.

Lot quality assurance sampling is a rapid survey method to assess the quality of coverage following a health intervention in pre-defined areas such as districts or sub-districts (called “lots”). It is used to determine whether the performance in each lot is above or below a predetermined threshold. While LQAS has traditionally been used with simple random sampling, cluster LQAS divides the sample into smaller clusters of a fixed number of units to increase the speed and efficiency of fieldwork (while trading-off precision of point-estimates, which are not the primary focus of this assessment).

The end-process assessment design is a retrospective cross-sectional household survey using cluster lot quality assurance sampling (cluster LQAS, or cLQAS) for household selection. Lots will be defined as districts (see section 2.3) and six clusters will be randomly sampled per lot. Data collection for the assessment will start four days after the end of distribution, to allow time for campaign ITNs to be aired, hung and used. Data analysis will include a formal classification of lots using LQAS rules based on the count of households receiving the correct/incorrect number of ITNs. Lots will also be ranked according to levels of ITN access and ITN use, to provide additional context for programmatic decision-making. Finally, levels of ITN access and use will be estimated at higher geographic scales.

Lot quality assurance sampling is a rapid survey method to assess the quality of coverage following a health intervention in pre-defined areas such as districts or sub-districts (called “lots”). It is used to determine whether the performance in each lot is above or below a predetermined threshold. While LQAS has traditionally been used with simple random sampling, cluster LQAS divides the sample into smaller clusters of a fixed number of units to increase the speed and efficiency of fieldwork (while trading-off precision of point-estimates, which are not the primary focus of this assessment).

## Assessment Sites

- Describe the geographic, health, or other relevant administrative units used for campaign microplanning.

- Describe the geographical scope and population included in the assessment (include a map).

- Describe whether the geographic scope has been defined according to specific parameters or reasons and what those are if so.

- Describe whether certain populations are targeted specifically for the assessment and the reasons if so.

- Ensure this section clearly describes any complex operating environments, if the assessment includes such areas.

The assessment will take place among communities living in 50 districts with differing malaria epidemiology and socio-economic profiles, distributed nationwide across the country’s 8 rural regions (comprising 8 of the 12 regions in the country). The four urban, low-transmission regions are excluded from the campaign and thus excluded from the assessment. The assessment sites correspond to all sites (regions and districts) that are included in the ITN campaign.

ITN campaign planning is based on the following mix of geographic and campaign-specific administrative levels: national, regional, district, sub-district, distribution point, household.

None of the areas identified for the assessment (or the campaign) are or include complex operating environments.

## Sample size

- Define the unit that will be the lot and the lots to be included in the sampling frame.

- Describe the use of the 6x10 sample design.

- State the expected number of clusters and households to be included.

- Describe the minimum level of aggregation for data and the corresponding minimum precision or maximum error associated with point estimates at this level.

For this assessment, “lots” will correspond to districts. The sampling frame will comprise the populations of all 50 districts in the 8 rural regions in the country. The sampling frame will be developed by combining ITN campaign microplanning data and will group populations in villages within sub-districts, within districts, within regions. The sub-district level, although present in the sampling frame, will not be used for sampling.

Sample size calculations for LQAS are based on estimating the minimum sample required to be able to classify lots with given levels of alpha and beta misclassification errors. AMP recommends the use of cLQAS sampling methods as defined by the Global Polio Eradication Initiative (GPEI).

This assessment will use the standard GPEI cLQAS design of six clusters with 10 households per cluster, i.e., 60 households sampled per lot (per district). Clusters will be taken as “villages” as defined in the sampling frame (some large villages have multiple entries in the sampling frame as microplanning requires multiple distribution points to service large population groups). This sampling design represents an acceptable trade-off between the risk of misclassification errors and workload/cost.

As the assessment will include 50 districts, this requires data collection in 300 clusters for a total sample size of 3,000 households.

While the primary purpose for using cLQAS is the classification of lots by performance, the sampling approach used in the assessment will permit data to be aggregated to produce point-estimates with sufficiently narrow confidence intervals for programmatic use at regional and national levels (for regions included in the assessment).

The minimum number of districts in a region included in the assessment is five. In these five districts, 300 households will be sampled. This sample size is sufficient to estimate regional-level point estimates with a maximum absolute error of ±8.0 percentage points, assuming a 95% confidence level and a design effect of 2.0.

## Sampling procedures

- Describe the procedures for cluster selection.

- Describe the process of random selection of households (how first and subsequent households are selected).

- Describe the procedures to be followed if household members are not at home or refuse to participate.

- Describe any additional sampling procedures as relevant to the country context.

### Stage one: selection of clusters

Six clusters will be randomly sampled per lot using probability proportional to size (PPS), with the village population as the measure of size. A list of villages and their respective populations will be created for each lot (district) and sorted alphabetically by village name. Six villages (clusters) will then be sampled by PPS.

While the use of PPS means each lot sample will be self-weighting, as part of the assessment procedures the total population count per lot will be available to weight aggregate results during analysis (i.e. for regional results).

### Stage two: selection of households

Within each selected cluster, 10 households will be selected using the following methodology. Assessment teams will begin by mapping the cluster and enumerating all households that are not obviously abandoned. If the number of households is greater than 25, the cluster will be repeatedly divided into segments of equal size (based on number of households) and sampled, until a segment with fewer than 25 households is created and selected. At each stage, segment selection will be made with equal probability using a random number generator phone app.

Once the cluster (or final segment) has fewer than 25 households, these households will be enumerated again and a random starting household selected from the phone app. The sampled household will be visited and invited to participate in the assessment. Regardless of the outcome of this first household visit (i.e. if consent is received to participate, if household members are not present, or if household members refuse) the next assessment household will be identified using the next-nearest-right-door method. Standing in front of the current house, teams will turn right and approach the nearest household in that direction. They will then repeat this a second time to arrive at the next-nearest door. The members of this household will be approached to participate in the assessment.

This process will continue until 10 household interviews have been completed in the cluster (i.e. if 2 households among the first 10 refuse to participate, then teams will visit 2 additional households using the same sampling approach to achieve 10 complete interviews in the cluster).

Basic household location information will be captured on all households approached to participate, including those with no (eligible) household members present and those whose household members refuse to participate. Households with no (eligible) household members present will be replaced by an alternate household – the assessment team will not make repeat visits to sampled households.

## Assessment questionnaire

- Describe:

  - The development and content of the assessment questionnaire.

  - The languages that the questionnaire will be translated into.

  - How the questionnaire will be pre-tested and how it will be finalized.

The assessment questionnaire is a tool focused on assessment objectives (rather than capturing contextual information). Most questions have closed response options. The questionnaire is adapted from generic templates in Word and ODK format (Excel) developed by AMP. Adaptations include renaming geographic units and editing some response options to match the campaign context. Questions on respondents’ exposure to SBC activities and knowledge of ITN campaign details have been revised with input from the NMP SBC focal point and SBC partners responsible for supporting campaign messaging.

The questionnaire comprises the following sections:

- Geographic location and household identification: region, district, cluster identifier, HH number

- Additional data to match assessment records with the HHR digital records (e.g. contact phone number for the household)

- Details of eligible residents at the assessment visit collected in a household roster, including ITN use the previous night and reasons for non-use when relevant

- Whether the household was visited by the HHR team and the number of eligible residents present during HHR (from participant recall)

- Number of campaign ITNs received

- Reason for any mismatch between the reported number of campaign ITNs received and the number that would be assigned based on applying campaign allocation rules to the count of eligible residents during HHR

- Number of ITNs from other sources owned by the household

- Knowledge of ITN distribution details prior to distribution occurring (timing, location, message sources)

Given the potential for recall bias of HH composition at the time of HHR (due to the time elapsed between the HHR team visit and the assessment visit) data on household composition and/or anticipated number of ITNs will potentially be captured through several questions. The generic template includes options for data capture from any written documentation shared by the HHR team, verbal guidance provided by the HHR team, and by participant recall of HH composition at the time of HHR. The final question choice will match the campaign approach taken during HHR (e.g. questions on written documentation will not be asked when leaving such documentation with the HH was not part of HHR procedures). Data on reasons for mismatches will be captured in both closed and open formats, to allow for greater detail to be provided by the assessment team where warranted.

The questionnaire has been developed in English. It will be translated to local language(s) following pretesting by NMP and partner staff. The final version will reflect input from pretesting and feedback from training.

## Assessment staff, recruitment and training

- Overall staffing structure:

  - Describe how the assessment will be coordinated and the staff that will be involved at each level, including field staff and team structure (assessors, supervisors, local guides, etc. as relevant).

  - Describe the role of the data analyst.

  - Describe the recruitment and selection process that will be followed where additional staff or technical support will be recruited.

  - Describe any technical or financial partners that will be engaged in the assessment(s).

- Training:

  - Describe the training that the field staff will receive including any post-training assessment.

### Staffing structure

Each district (lot) will have its own assessment team comprising one technical lead and one community liaison staff. Team members will work together to liaise with community representatives, map and select households, conduct household visits and administer the questionnaire. Geographic groups of five assessment teams will be overseen by an assessment supervisor (10 supervisors for 50 teams) who will support assessment teams remotely and in-person. Supervisors will share daily feedback on data quality and completeness with teams and be responsible for taking corrective action to reduce data collection errors. The assessment will be led by a national assessment coordinator who is a monitoring and evaluation professional with expertise in planning and implementing digital data collection. A national data analyst will be responsible for developing and finalizing the digital data collection tool, daily data processing and analysis, and sharing feedback with the assessment teams via the coordinators.

In total, the assessment team will comprise one national assessment coordinator, one national data analyst, 10 supervisors and 50 teams of two assessors at the community level (100 assessors).

### Recruitment

Experienced assessment supervisors will be hired or nominated for their role of ensuring assessment quality. Supervisors may be selected from independent partners who are not involved in the campaign, such as non-governmental organizations (NGOs) or universities, WHO, UNICEF or other technical partners.

The two assessment team members will be recruited locally to their assigned districts, to the extent possible, to ensure familiarity with local geography and culture. Recruitment will consider gender equity, language ability, minimum education level, previous experience of similar activities, availability, and personal attributes such as integrity and approachability. As data will be collected by electronic data collection, ownership of a phone meeting minimum hardware and software specifications will be a condition of recruitment for assessors.

Where selected assessors are less familiar with the geographical area, local guides may be recruited to support assessment teams. Local guides may also be recruited in areas where the cultural context could make it difficult for assessors from outside the area to gain the trust of household members to allow entry into homes and to respond openly to survey questions.

### Training

A four-day in-person training course for assessment supervisors will be held in a central location, led by the assessment coordinator and data analyst, with input from ITN campaign leadership and technical partners. The training agenda will cover the following components:

- Overview of the ITN campaign and HHR activities, including definitions and eligibility criteria to be applied during HHR

- Overview of ITN distribution activities, including actions required by household members to receive ITNs and ITN distributor roles and responsibilities

- Overview of the assessment design and household sampling procedures

- Discussion of informed consent and good assessment practices

- Review of instructions for each step of the assessment, including hands-on exercises

- Review of the content of the assessment questionnaire on paper

- Introduction to and practice with the digital questionnaire and software

- Troubleshooting common software and hardware challenges

- Practical session in a community outside the assessment sampling frame to practice mapping, sampling, and questionnaire administration.

- Practical session on conducting training and adult learning principles.

Individual assessment supervisors will then cascade this training to their assessment teams. Part of this training will include initializing the data collection software on assessor’s phones. Software will be set up such that data is erased from the phone following a successful transfer to the assessment server.

## Field procedures

- Describe the timing and duration of fieldwork.

- Describe the main fieldwork procedures, including how the questionnaire will be implemented.

- Describe the process for submitting data and maintaining data security during fieldwork.

- Describe approaches to supervision and monitoring.

Fieldwork will begin on or after the fourth day following completion of campaign ITN distribution activities. The exact timing of fieldwork will thus depend on ITN distribution timing. ITN distribution is currently scheduled to take place from date to date. Fieldwork will last six days per district, with all districts running concurrently; each district team will complete one cluster of ten households per day, for a total of 60 households per district over six days.

### Preparation for cluster entry

Cluster random sampling will be performed in advance by the data analyst and district cluster lists will be shared with assessment supervisors during their centralized training. Supervisors will have the opportunity to liaise with campaign HHR and distribution teams prior to fieldwork to gather basic information about the selected clusters, such as confirming the location (if required) and boundary, area description, and approximate number of households.

During supervisor cascade training for their assessment teams, fieldwork plans will be developed for each district describing the order in which clusters will be visited. Prior to fieldwork the assessment teams and supervisors will contact local community leaders in each cluster – using details shared by the HHR and/or ITN distribution teams – to facilitate assessment teams’ arrival in each community.

### Household consent and interviews

After community entry and the selection of the starting household (section 2.4.2), the household will be visited and invited to participate in the assessment. The assessment team will request to interview the household member who spoke to the HHR team when they visited (assuming the household was registered by the HHR team); this is to minimize recall bias arising from interviewing someone who was not involved in the HHR team visit. If the person who spoke to the HHR team is not available or household members refuse to participate, a record of the household approach will be made in the digital tool and the household replaced.

Before the interview begins, the respondent(s) will be informed about the purpose of the assessment verbally in their preferred language. The respondents will be specifically informed that participation is voluntary and that they may refuse at any time. Once consent is obtained the interview will be carried out.

The household sampling method will be repeated until 10 full interviews have been completed in the cluster.

### Data collection and data management and safety during fieldwork

Data will be collected by electronic data collection, using KoboCollect software or similar with offline capabilities installed on phones belonging to members of the assessment team. Ownership of a phone meeting minimum hardware and software specifications will be a condition of recruitment for assessors. Assessment leadership will draw on the growing lessons learned on the use of “bring your own device” approaches for digital campaign activities. The digital tool will include detailed relevance criteria, logic checks, skip patterns and required (i.e. non-missing) responses, to maximize the completeness, internal consistency and overall quality of data collected at source. Depending on local connectivity, data from each interview will be uploaded to the assessment server following each interview or once 10 interviews have been completed and the team can connect to a data network. Assessment teams will carry 20 printed questionnaires for use in case of technology failure – sufficient to complete two clusters while awaiting IT support. Supervisors will have additional paper copies to distribute if required.

The software on assessors’ phones will be set-up such that all locally held data is permanently erased once a record is submitted to the server. Furthermore, assessors will not have read access to the assessment server so records cannot be downloaded to personal phones.

Collection of personally identifying information at consenting households will include the capture of household GPS coordinates and first names and ages of household members. If digital matching is used to link assessment records to HHR records and/or ITN distribution records, teams will additionally capture the full name of the head of household, a phone number associated with the household, and any ID numbers or codes associated with the HHR process.

### Supervision and monitoring

Assessment supervisors will observe assessor teams during fieldwork, aiming to complete 2-3 team visits per day so that all teams receive supervision in the first two days of data collection. Supervisors will provide direct feedback in response to observations to help assessors improve their approach for subsequent household visits and interviews. Time permitting, supervisors will revisit a small number of completed households to do a short interview and compare the assessors’ results with the supervisor’s notes.

In the evening of a fieldwork day, or early next morning before the next assessment work begins, the supervisor will contact each of their assessment teams by phone, digital call, or in-person, and debrief with each team on their progress. Assessment teams will share lessons learned, concerns and positive feedback from the field; the supervisor will provide feedback on the completeness and quality of data collection using information provided by the data analyst.

Assessment supervisors will provide a summary of any significant issues to the assessment coordinator and will keep notes of their observations to discuss during the stakeholder meeting and include in the final assessment report.

For technical issues with assessors’ phones and software that supervisors are unable to resolve, national-level IT and M&E consultants will be on stand-by for remote support.

## Data management and analysis

- Describe the approach to data management and analysis, including:

  - Management of data privacy and security, including whether and how data are encrypted during transmission and storage

  - Approach for data processing and analysis, including the analysis plan

  - Approach for the classification of lots

- Describe the process for data review, including:

  - How results will be reviewed in real-time, and feedback shared with assessment teams (on data quality) and HHR teams (on HHR performance)

  - How lots will be identified for further investigation

  - Timeline for reporting assessment findings

### Management of data private and security

The data collection software installed on assessors’ phones will be set up with server write access only; all locally held data will be permanently erased once a record is submitted to the server. Server access will be controlled by passwords with access rights defined by the national data analyst in consultation with the assessment coordinator. Once the analyst has confirmed that all assessment data has been uploaded to the server and a copy of the full data set made to an offline storage location (e.g. the hard drive of the analyst’s laptop), the analyst will deactivate server access for assessors and supervisors. Assessors may keep the software on their personal phones, but they will not be able to download forms or upload new data. Only the data analyst and assessment coordinator will have read/write access to the full server data. Following data matching (to the HHR records and/or ITN distribution records, if applied) and data cleaning, first names (and full names and phone numbers if captured for data matching) will be removed so that analytical data files only include GPS points as data from which to potentially identify households.

Following analysis, GPS values will be replaced with data representing the centroid of the respective cluster (i.e. all 10 households from the same cluster will have the same GPS data). These cluster centroid values will then be randomly jittered within a 2km x 2km square around each centroid, so that the final GPS values in the data represent approximate locations of households included in the analysis within a 4 km2 area.

### Data processing and analysis

Data will be transferred from data collection software installed on assessors’ phones to a central server space dedicated to the assessment, as described above. Data processing will occur daily during fieldwork as part of data quality assurance. Full data processing and analysis will occur once fieldwork has been completed. All data processing and analysis will be performed in the R or Stata statistical software packages, using replicable code adapted from templates provided by AMP. One script will be used to review the raw data and perform consistency checks and reversible cleaning where warranted, a second script will perform different standard analyses, and a third script will partially automate the production of results for the assessment report.

Daily data processing for quality assurance will focus on the completeness and quality of submitted data. Checks for missingness, out-of-range values and internal inconsistency will be performed, though the ODK form will be designed to minimize such errors. The analyst will share daily feedback on team performance with assessment supervisors, who will discuss feedback with their teams and take actions to support and improve data collection quality where necessary. Communication between teams will primarily take place by WhatsApp and email. Two WhatsApp group chats will be set up for the assessment team: one including all team members and one restricted to the supervisors, analyst and coordinator.

Assessment analysis will proceed once all data has been collected. Analysis will involve formal and informal lot classification (defined based on whether LQAS decision rules are used for classification) and the calculation of indicators at district, region and national levels (representing regions included in the campaign). Results will be variously presented in tables, charts and maps.

#### Lot classification

Formal lot classification will involve the application of LQAS decision rules to classify district ITN distribution performance. Classification will be based on the indicator, the number of households that received an incorrect number of campaign ITNs when compared to the number that should have been assigned based on applying the campaign allocation rules to the count of eligible household members recorded during household registration and use the GPEI classification approach. The table below presents the classification approach based on the stated sample decision rules, and the equivalent classification range corresponding to the population lot value. Decisions rules are set to reduce misclassification of a lot into a ‘better’ performance category by ensuring alpha and beta errors for the estimate of population coverage are both lower than 10%.

Table 1 LQAS classification approach

| Classification | Decision rule (lot sample, 60 households) | Classification range (lot population) |
| --- | --- | --- |
| Good | 0 – 3 households with incorrect counts | ≥ 90% |
| Uncertain | 4 – 8 households with incorrect counts | > 80% to < 90% |
| Inadequate | 9 or more households with incorrect counts | ≤ 80% |

In this system, lots classified as “Good” have no suggested performance gaps and require no action; lots classified as “Inadequate” are likely to have serious performance gaps and are a priority for investigation that can lead to recommendations to improve future performance; lots classified as “Uncertain” may have performance gaps but response is a lower priority than the “Inadequate” category.

Informal lot classification will involve ranking districts based on one or more of five indicators selected to represent key outcomes expected from the ITN campaign. These indicators are:

- Percentage of households that received at least one campaign ITN

- Percentage of households that received the correct number of campaign ITNs (based on household size and eligibility criteria for the campaign)

- Percentage of the population that has access to an ITN (assuming each ITN can be used by two people)

- Percentage of the population that reported sleeping under an ITN the previous night

- Percentage of children under five that reported sleeping under an ITN the previous night

Each indicator will be estimated at the district level and presented in tabular format alongside the formal lot classification indicator. An example output is shown below.

Figure 1 Example lot classification table

#### Secondary analysis, including region and national level

To support and complement lot classification, descriptive univariable analysis of secondary indicators will be performed at different geographic levels. The household (or respondent) is the primary unit of analysis and results will be calculated for each lot (collection of 60 households) and aggregated to higher administrative levels (e.g. region and national). Since clusters are selected using PPS with a sample of households per cluster, lot-level results are self-weighting. Confidence intervals will not be calculated around lot-level point estimates as the sample size is too small to yield confidence intervals with reasonable width for management decision making.

Percentage outcomes at regional level (and above) will be calculated for all regions with at least 4 districts, or 240 complete household interviews from 24 clusters. This is a sufficient sample to estimate results with a precision of at most 10 percentage points, assuming a maximum design effect of 2.5. When combining districts for regional-level estimates, data will be assigned weights using the corresponding district population. That is, households in district J of region K will have weights as follows:

Household weight in district J = Population of district JPopulation of region K

Should an estimate of a geographic area above the region be required (e.g. a summary result for all regions participating in the campaign), household-level data in region K will further be weighted by the population of region K divided by the total population of the larger aggregate area (e.g. of all regions participating in the campaign).

Calculation of standard errors will account for the clustered nature of the data.

The table below presents indicators grouped by theme and indicates at which level results will be estimated. Given the uncertainty associated with lot-level results, only indicators critical to decision-making will be presented at this level.

Table 2 End-process indicators and the levels at which they are estimated

| Indicator | Level of aggregation |  |  |
| --- | --- | --- | --- |
|  | District | Region | National |
| HHR outcomes |  |  |  |
| Percentage of households that report being visited by a HHR team | x | x | x |
| Reasons why households were not visited by a HHR team | x | x | x |
| ITN distribution outcomes |  |  |  |
| Percentage of households that received at least one campaign ITN | x | x | x |
| Reasons why households did not receive any ITNs from the campaign | x | x | x |
| Percentage of households that received the correct number of campaign ITNs | x | x | x |
| Reasons why households received an incorrect number of campaign ITNs | x | x | x |
| ITN supply |  |  |  |
| Percentage of campaign ITNs received that are still in the household’s possession |  | x | x |
| Percentage of households with at least one ITN from sources other than the campaign |  | x | x |
| ITN population access |  |  |  |
| Percentage of the population that has access to an ITN from any source (assuming each ITN can be used by two people) | x | x | x |
| Percentage of the population that has access to a campaign ITN, assuming each ITN can be used by two people |  | x | x |
| Percentage of the population that has access to an ITN from sources other than the campaign, assuming each ITN can be used by two people |  | x | x |
| ITN use |  |  |  |
| Percentage of campaign ITNs used for sleeping under the previous night |  | x | x |
| Percentage of ITNs from sources other than the campaign used for sleeping under the previous night |  | x | x |
| Percentage of the population that reported sleeping under an ITN the previous night | x | x | x |
| Percentage of children under five years that reported sleeping under an ITN the previous night | x | x | x |
| Percentage of pregnant women (by self-report) that reported sleeping under an ITN the previous night |  | x | x |
| Reasons why individuals did not sleep under an ITN the previous night |  | x | x |
| ITN distribution knowledge |  |  |  |
| Percentage of respondents that were aware of the date and location of the ITN distribution before it took place |  | x | x |
| Sources of information about the ITN distribution |  | x | x |
| ITN SBC exposure |  |  |  |
| Percentage of respondents who report receiving information from the distribution staff about ITNs or malaria |  | x | x |
| ITN messages received, among respondents who were exposed to messages |  | x | x |

### Data review and response, including lot investigations

ITN campaign and assessment leadership will use the formal and informal lot classification, and supporting results, to identify districts that exhibit ideal distribution performance (and population ITN behaviors) and those with suboptimal performance. It is anticipated that, at a minimum, all lots classified as “Inadequate” for accurate ITN distribution will undergo investigation. Investigation will consider:

- Geographic and socio-economic characteristics of target lots and how these differ from better performing lots;

- Level of experience of HHR team members and other relevant contextual factors not present in the assessment data;

- Level of experience of ITN distribution team members and other relevant contextual factors not present in the assessment data;

- Review of ITN supply and distribution records to identify any logistic failings such as stockouts or misallocated nets.

- Patterns in the reasons given for errors and differences between poor and better performing lots;

- Geographic clustering of poor performance and its relation to the above factors.

Lot investigation may also consider lot-level results on ITN access and use, particularly cases where one or both measures are very low relative to regional or national averages. Results on the reasons for non-use of ITNs, levels of pre-campaign knowledge about the distribution, and common message sources, could all inform NMP plans for tailored post-campaign SBC activities.

The aim of the lot investigation is to identify any underlying factors which may be associated with poor performance trends, so that campaign leadership can take steps to address these issues for future campaigns. Actions could include, for example, the intensification of supervision plans for future distributions in areas that meet certain geographic or socio-economic criteria, or targeted SBC interventions in areas with relatively low levels of ITN use despite adequate access to ITNs.

## Reporting and data archiving

- Describe the process and timelines for disseminating results to national and sub-national programme offices, survey participants, implementing partners and other key stakeholders as relevant, for validation.

- Describe how data will be made available for secondary data analysis.

### Final reporting

Assessment results will be compiled and discussed during a stakeholder meeting, to be conducted within two weeks of the end of the assessment. Campaign leadership, assessment teams and technical partners will attend the meeting. Participants will review and discuss key findings and results; review results from lot investigations; and discuss recommendations to be implemented before the next ITN distribution activity. Feedback from the meeting discussion will be included in the final assessment report.

An assessment report will be developed by the analyst and coordinator shortly after the stakeholder meeting. The report will be structured with sections on background, assessment methods, assessment results, recommendations, and discussion. The report will be validated by the campaign M&E subcommittee prior to broader dissemination. The final report will be shared with national malaria and ITN campaign stakeholders, and with relevant MoH departments for whom lessons learned on health campaign implementation may be of interest. The report will be shared through international partnerships (such as AMP) so lessons learned can be shared across countries.

### Data availability

The fully deidentified and jittered data sets will be maintained by the NMP M&E team and will be available for secondary analysis on request and on submission of an analysis plan.

# Ethical Considerations

- Note whether national ethical clearance is required for the assessment, and if not, why not. If ethical clearance is required, name the independent review board (IRB) and describe the process to be followed.

- Describe the process of obtaining informed consent to participate.

- Describe the risks to participants and the process of maintaining participant privacy and removing identifying information.

The proposed study will be conducted according to the principles of the Declaration of Helsinki and the International Guidelines for Ethical Review of Epidemiological Studies.

This study has been designed to address the ethical principles of respect for persons, beneficence, and justice. Efforts are made to protect individual autonomy, minimize harm, and maximize benefits and equitably distribute risks and benefits by using procedures which are consistent with sound research designs that take these issues into consideration. Since this is exclusively an interview survey and does not take samples of any kind, minimal risk is expected for the participants.

This assessment will be submitted to the name of IRB / ethics committee for screening and determination of whether it meets the definition of human subjects research. If it meets the definition, the assessment will be initiated only after receiving written approval from the IRB.

## Informed consent

The assessment team will request to interview the household member who spoke to the HHR team when they visited (see 2.7.2). Assuming this household member is available, they will be informed about the purpose and nature of the assessment, what participation in the study requires, possible risks and benefits, and protections. Participants will also be informed of their right to not participate in the assessment or to withdraw from the study or not answer any questions they do not feel comfortable asking. Respondents will be provided with contact information for the assessment coordinator. The above information will be conveyed to participants in either English or list other languages used in the assessment. Verbal consent will be obtained for all participants before the assessment begins.

The above processes will be implemented regardless of the IRB determination of human subjects research.

## Risks to participants and response

Potential Risks

Potential risks to assessment participants are breach of confidentiality. In this assessment, a breach of confidentiality could occur if i) private and sensitive information from interviews could be linked to a household or individual respondent and this information was obtained by person(s) outside of the assessment team, or ii) something a participant says is heard or found out by someone else.

Strategies to Address Risks

The informed consent procedure will clearly describe the information to be requested by the assessment team and the questions that will be asked. The team will explain the need to record first names and ages of household members to help ascertain the number of eligible household members.

Data collection devices will be set so that no data is stored locally on the device once it has been successfully submitted to the server. All data and other information will be maintained confidentially and anonymous to the greatest extent possible. During data collection and analysis, data sets will be stored in secure locations with password protection and clearly defined access rights (on a secure server and on assessment staff laptops).

For participating households, household GPS location and household members' first names and ages will be recorded in the raw data files. If assessment data are to be matched to the HHR records and/or ITN distribution records, the full name of the head of household and a phone number associated with the household will also be recorded. All matching variables will be dropped during data preparation once assessment records have been merged with HHR and/or ITN distribution records. Names will be dropped during data preparation so that the only potentially identifying information in the analysis data are household GPS coordinates (used for generating maps). GPS values will be replaced by cluster centroids and jittered in the final data set, such that the final data will contain no personally identifying information nor precise GPS values.

Participants will be encouraged to contact assessment supervisors or the assessment coordinator to discuss any concerns they might have.

Data reporting

All data based on this research will be reported in aggregate form or stripped of individual identifiers. No individual respondents or households will be identified.

Staff Ethical Training

All assessment staff will be trained in human subjects protection, especially the importance of gaining informed consent and protecting privacy and confidentiality.

## Beneficence (Maximizing Benefits and Minimizing Harm)

There is unlikely to be any direct benefit to participants themselves at the time of the assessment or immediately after. However, the assessment will result in knowledge that can be used to improve planning and implementation for future ITN distributions, thus benefiting households in areas targeted for future distributions (which could include the areas visited for this assessment). In addition, data used to inform post-campaign activities such as targeted SBC interventions may indirectly benefit participating households through better design and targeting of activities.

Output from this assessment will not be directly provided to community members.

# Collaborators and funding mechanisms

- Indicate primary implementing agency.

- Provide names and affiliations of key roles and involvement in bullet format or table format. This will include the following:

  - Assessment coordinator

  - Assessment data analyst

  - Any additional data manager roles

  - External experts

  - National stakeholders

  - International stakeholders

  - Funding agencies

- Include information on ITN campaign M&E sub-committee and assessment technical working group where relevant.

- Detail any other human resources needed to implement the assessment.

Implementation of the assessment will be jointly conducted by all partners in the roles indicated below. While all partners will provide input into assessment design, the primary implementation agency will be name of implementing agency under the guidance of oversight agency.

Table 3 Partner roles and responsibilities

| Role | Name | Affiliation |
| --- | --- | --- |
| Coordinator |  |  |
| Data Analyst |  |  |
| IT Systems Admin |  |  |
| External Quality Assurance |  |  |
| External Technical Expert |  |  |
| External Technical Expert |  |  |
| Oversight Lead |  |  |
| Technical Partner |  |  |
| Technical Partner |  |  |
| Technical Partner |  |  |
| Funding Partner |  |  |
| Funding Partner |  |  |

Additional content omitted for this section.

# Budget

- Provide a summary of the budget by cost category and indicate the total cost for the assessment.

- Note the funding source(s) and/or funding mechanism(s).

A summary of the budget by cost and activity categories is presented below.

|  |  | Activity categories |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Preparatory phase |  |  | Implementation | Data analysis and reporting |  |  |  |  |
| Cost category | Subcategory | Recruitment | Survey design and testing | Training | Fieldwork | Lot classification | Additional analysis | Stakeholder meeting | Report writing | Dissemination |
| Personnel | Salaries |  |  |  |  |  |  |  |  |  |
|  | Per diem |  |  |  |  |  |  |  |  |  |
| Travel | Per diem |  |  |  |  |  |  |  |  |  |
|  | Lodging |  |  |  |  |  |  |  |  |  |
|  | Transport |  |  |  |  |  |  |  |  |  |
| Equipment | Hardware |  |  |  |  |  |  |  |  |  |
|  | Software |  |  |  |  |  |  |  |  |  |
| Consumables | Office supplies |  |  |  |  |  |  |  |  |  |
|  | ID cards and clothing |  |  |  |  |  |  |  |  |  |
| Other direct costs | Printing |  |  |  |  |  |  |  |  |  |
|  | Communication |  |  |  |  |  |  |  |  |  |
|  | Translation |  |  |  |  |  |  |  |  |  |
| TOTAL COSTS |  |  |  |  |  |  |  |  |  |  |

Additional content omitted for this section.

# Timeline

- Provide a schedule and timeline of all assessment activities in table or Gantt chart format.

The anticipated study timeline is outlined below for key tasks.

| Activity | Timing | Months or weeks from distribution |  |  |  |  |  |  |  | Assessment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Responsible | -5M | -4M | -3M | -2M | -1M | -1W | 1W | 2W | +1W | +2W | +3W | +4W | +5W | +6W | +7W |
| Preparatory Phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruit national assessment staff | NMP | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Decide on digital matching approach (if used) | NMP |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft protocol and tools | Assessment Staff |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Share protocol and tools for partner review | NMP |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Incorporate partner comments and finalize | Assessment Staff |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit protocol for ethical review (if required) | Assessment Staff |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Source microplanning data for sampling frame | Assessment Staff |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Draw samples of six clusters per district | Data analyst |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Set-up online assessment server | Data analyst |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Programme and test digital assessment tool | Data analyst |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Translate digital assessment tool | NMP |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Adapt training and fieldwork materials | Assessment Staff |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Recruit sub-national supervisors | Coordinator |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Train sub-national supervisors centrally | Assessment Staff |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Recruit assessment team staff locally | Supervisors / NMP |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Cascade training to assessment teams | Supervisors |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| ITN distribution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Planned distribution timing | Campaign teams |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |
| Assessment Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assessment fieldwork | Assessment Team |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Daily data quality review | Data analyst |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Data quality feedback to assessment teams | Supervisors |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Analysis and Reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Full assessment data processing | Data analyst |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Lot classification | Data analyst |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Additional analysis | Data analyst |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Lot investigation | NMP |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Stakeholder meeting | Coordinator |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |
| Draft assessment report | Coordinator / Analyst |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |
| Report validation | NMP |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |
| Report finalised and disseminated | Coordinator / Analyst |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |

# Bibliography

- Include a bibliography or list of references used to develop the assessment protocol.

- Alliance for Malaria Prevention (AMP). Case study: Digitalization of the 2020 and 2023 mass ITN campaigns in Togo: the experience of bring your own device (BYOD). November 2024.
https://allianceformalariaprevention.com/wp-content/uploads/2024/11/Togo_CaseStudy_BYOD_112024_EN.pdf

- Global Polio Eradication Initiative (GPEI). Assessing Vaccination Coverage Levels Using Clustered Lot Quality Assurance Sampling. Field Manual. Version Edited for the Global Polio Eradication Initiative (GPEI). April 27, 2012. 
https://polioeradication.org/wp-content/uploads/2016/09/Assessing-Vaccination-Coverage-Levels-Using-Clustered-LQAS_Apr2012_EN.pdf

- Pezzoli, L., N. Andrews, and O. Olivier Ronveaux. “Clustered Lot Quality Assurance Sampling to Assess Immunisation Coverage: Increasing Rapidity and Maintaining Precision.” Tropical Medicine and International Health 15, no. 5 (May 2010): 540–546. https://doi.org/10.1111/j.1365-3156.2010.02482.x.

- Okayasu, H., A. Brown, M. Nzioki, A. Gasasira, M. Takane, P. Mkanda, S. Wassilak, and R. Sutter. “Cluster Lot Quality Assurance Sampling: Effect of Increasing the Number of Clusters on Classification Precision and Operational Feasibility.” Journal of Infectious Diseases 210, suppl. 1 (November 1, 2014): S341–S346. https://doi.org/10.1093/infdis/jiu162.

- Zegers de Beyl C., Koenker H., Acosta A., Onyefunafoa E.O., Adegbe E., McCartney-Melstad A., et al. “Multi-country comparison of delivery strategies for mass campaigns to achieve universal coverage with insecticide-treated nets: what works best?” Malaria Journal 2016; 15:58
https://doi.org/10.1186/s12936-016-1108-x

# Annexes

- Include a list of all annexes which may include but are not limited to:

  - Assessment questionnaire, including translations

  - Participant information sheets

  - Participant consent forms

  - Other supporting documents (e.g. sub-national notification letters, etc.)

  - Additional documents required by national IRB if ethical review is required or being sought

# Assessment questionnaire

Generic questionnaire in Word available at https://github.com/edsternberg/clqas-tools.

# Participant information sheet

END-PROCESS ASSESSMENT OF ITN CAMPAIGN HOUSEHOLD REGISTRATION
COUNTRY AND/OR LOCATIONS, YEAR

PARTICIPANT INFORMATION SHEET

SPEAK TO THE HOUSEHOLD HEAD

[Greeting]

My name is _________ and this is _________.

We are working in collaboration with the National Malaria Programme to assess the performance of the recent ITN campaign, which you might be aware of. We are visiting your community today and would like to collect information from 10 households like yours.

Before we go further, can I just check:

- Are you at least 18 years old?

- Have you been staying here for at least the past one month? This is to ensure the respondent was in the community when HHR occurred – users can adjust timing as required.

- Are you the head of this household?

  - If the respondent is not the household head, ask to speak to the household head

- Are you free to talk with me today?

What is the assessment about?

We are checking on the work performed by teams working for the ITN campaign. This includes the teams that registered households for the ITN campaign a few weeks ago and the teams managing the ITN distribution last week. We are also interested in understanding how your household is using any ITNs that were received from the recent ITN distribution.

What questions will you ask?

If you agree to participate, we will ask you some questions about the members of your household, including their first name and their age. We will ask about the use of ITNs for sleeping under. For the women in your household between the ages of xx and yy we will ask if they are pregnant. This is to help us estimate how many pregnant women sleep under ITNs.

We will also ask questions about the campaign activities, such as whether your household was registered and whether you received ITNs from the distribution. You can still participate if your household wasn’t registered or if you didn’t receive any ITNs. To get accurate information, we would like to speak to the person who interacted with the registration team when they visited (if they visited). The discussion usually takes about 15 minutes.

Do I have to take part?

Your participation is voluntary and you do not have to agree to take part. There will be no consequences for you or your household if you do not take part.

What will you do with the information?

If you do take part, all the information we collect will remain confidential. That is, your name and the other information we collect will not be shared with people outside the assessment team. Before the data are analysed, we will remove the names and phone number(s) from the data.

Is there any benefit to me or my household if I take part?

There will be no direct benefit to you from participating. We do not have any ITNs to give to households. However, the information that you provide will help the National Malaria Programme and its partners understand what went well and what needs to improve when planning and doing ITN campaigns. These lessons should help improve future ITN campaigns so that as many households as possible receive the ITNs they are assigned. If you have any questions about malaria, mosquito nets or the campaign, we’ll be able to answer those.

What if I have questions about the assessment?

If you have any questions or concerns about taking part, you can ask us now.

If you have any questions after we leave, you can talk to the assessment coordinator using this contact information:

Assessment coordinator’s contact details Name: Contact:

You will be given a copy of this Information Sheet

You may either read this form yourself or I will read it to you.

# Participant consent form

In this example case, the HHR in-process assessment determined that HHR coverage was >99% for campaign areas and thus the microplanning documents are the preferred sampling frame source as their use is likely to be less biased than using projected census data. Users will need to determine the most appropriate sampling frame in their case, noting that the choice to use microplanning data should consider its likely coverage.

Global Polio Eradication Initiative (GPEI). Assessing Vaccination Coverage Levels Using Clustered Lot Quality Assurance Sampling. Field Manual. Version Edited for the Global Polio Eradication Initiative (GPEI). April 27, 2012.

Okayasu, H., A. Brown, M. Nzioki, A. Gasasira, M. Takane, P. Mkanda, S. Wassilak, and R. Sutter. “Cluster Lot Quality Assurance Sampling: Effect of Increasing the Number of Clusters on Classification Precision and Operational Feasibility.” Journal of Infectious Diseases 210, suppl. 1 (November 1, 2014): S341–S346.

Alliance for Malaria Prevention (AMP). Case study: Digitalization of the 2020 and 2023 mass ITN campaigns in Togo: the experience of bring your own device (BYOD). November 2024.